Millom Without Parish Council

Community Plan - MONITORING Report – Annual Review held on 18th May 20

Approved at the Parish Council meeting held on – 1st June 2020

|  | MWPC Community Plan Monitoring Report 18th May 2020 | Target Date | Lead Councillors | Who Is working on the Action? | Project Budget | Allocated or spent to date | Balance to spend | DELIVERY OVERVIEW | RAG STATUS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A. | Connecting Our Communities |  |  |  |  |  |  | Narrative Updates by Action |  |
| A1 | Enforcement of Speed Limits |  |  |  |  |  |  |  |  |
| 1 | Through the Parish Council Traffic Management Team continue to lobby for new speed limits and action to reduce speeds through our communities. | March 21 | David / Gaby / Ian | PC and CCC Highways |  |  |  | Meetings held with CCC Highways – need to seek approval from CCC to place speed devices – work ongoing | Significant delays expected due Covid-19 |
| 2 | Working with Ghyll Scaur Quarry Liaison Committee, gain funding approval to purchase mobile speed devices | Completed | David / Gaby / Ian | PC and GSQLC |  |  |  | Funding approved in principle by GSQLC | Completed |
| 3 | Working with CCC Highways to seek the appropriate approvals and to agree the best options for deployment of mobile speed devices. | March 21 | David / Gaby / Ian | PC and CCC |  |  |  | Approvals to be sought via CCC Highways and Local Area Committee for Copeland | Significant delays expected due Covid-19 |
| 4 | Working with other Parish Councils to identify what actions have been taken in other | Sept 21 | David / Gaby / Ian | PC via CALC |  |  |  | Contact to be made with CALC to seek information as to what other Parish Councils have implemented. | Work Underway |
| A2 | Litter |  |  |  |  |  |  |  |  |
| 1 | Set up a Group of Volunteers to undertake targeted litter picks within Millom Without | Completed | Adrianne | PC | £250 | £100 | £150 | With local community support a number of litter cleaning events across the Parish have been undertaken. Other events are limited by Covid-19 | Completed |
| 2 | Review the range and positioning of Litter Bins within Millom Without | March 21 | Adrianne | PC and CBC | £250 | £100 | £150 | One new bin has been positioned at the Lay By (Buckman Brow). Two other bins planed for Pinnal Hole and on the road near the Railway Station. | Delays likely due to COV19 |
| A3 | Connecting our Communities with Paths and Cycle Ways |  |  |  |  |  |  |  |  |
| 1 | Set up a meeting of interested parties from the Community Plan Feedback Meeting (Feb 19) and explore and prioritise ideas to be taken into a plan of action. | Completed | Angela/ Pauline/ Adrianne | PC and APIT |  |  |  | Team now set up and actively looking at options | Completed |
| 2 | Pathway from the Hill to The Green | 2021 | Angela, Pauline and Marg (Steering Group) | PC and CCC |  |  |  | Significant work undertaken in partnership with CCC footways team to look at upgrading “Middlecut”. Work on a direct route from The Green to The Hill also remains on the table given recent push by HMG on cycle routes | Significant delays expected due Covid-19 |
| 3 | Guided Cycle Routes | 2021 | Adrianne | PC |  |  |  | Events were planned for early 2020 but paused by Covdi-19 | Delays likely due to COV19 |
| 4 | Cycle Workshops | 2021 | Adrianne | PC |  |  |  | Events were planned for early 2020 but paused by Covdi-19 | Delays likely due to COV19 |

| A4 | English Coastal Path |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Working with other Partners to extend the English Coastal Path which will seek to connect Millom Without to Duddon Bridge and Broughton In Furness | Jan 20 | David | PC, SCP, DEP, CCC and CBC |  |  |  | PC made submission to Natural England in Jan 20 and encouraged residents to make their voice heard. Now await outcome of Government review | Completed |
| A5 | Heritage and Tourism |  |  |  |  |  |  |  |  |
| 1 | Working with identified Delivery Partners to create a potential heritage trail within the area of Millom Without. | 2021 | Adrianne/ Pauline and Brian | PC and Local Volunteers |  |  |  | Some initial work undertaken and is being reviewed by the team. Local volunteers are needed to help with this project. | Delays likely due to COV19 |
| 2 | Improve the Signage of Heritage Sites, Paths and Cycle ways to promote access and enjoyment | 2021 | Adrianne/ Pauline and Brian | PC and Local Volunteers | £900 |  | £900 | Some initial work undertaken and is being reviewed by the team | Delays likely due to COV19 |

|  | MWPC Community Plan – Monitoring Report 18th May 2020 | Target date | Lead Councillors | Who Is working on the Action? | Project Budget | Allocated or spent to date | balance to spend | DELIVERY OVERVIEW | RAG STATUS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| B | Connectivity – Mobile and Broadband |  |  |  |  |  |  |  |  |
| B1 | Mobile and Broadband Accessibility |  |  |  |  |  |  |  |  |
| 1 | APIT will collate information on existing coverage and service providers for mobile and broadband and establish a strategy to improve householder’s access | 2020 | Nick | PC and APIT |  |  |  | Strategy has been developed and shared with PC to support roll-out of resident workshops, once Covid-19 regulations are updated for public gatherings. | Completed |
| 2 | APIT will disseminate information regarding the existing level of services and the alternatives for accessing these. | 2020 | Nick | PC and APIT |  |  |  | Roll out is dependent on the lifting of Covid-19 regulations | Delays likely due to COV19 |

|  | MWPC Community Plan – Monitoring Report 18th May 2020 | Target date | Lead Councillors | Who Is working on the Action? | Project Budget | Allocated or spent to date | balance to spend | DELIVERY OVERVIEW | RAG STATUS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C | Child Friendly Places |  |  |  |  |  |  |  |  |
| C1 | Spaces for Young Children |  |  |  |  |  |  |  |  |
| 1 | APIT to work with interested residents to explore ideas and opportunities to improve and enhance access for spaces specifically focussed on young children. | Completed | Angela, Pauline, Lesley and Nick | PC and APIT |  |  |  | Team have created an outline plan and engaged with Contractors to develop ideas. Discussions with Thwaites Village Hall have secured a commitment to place a Play Area on the Playing Fields. | Completed |
| 2 | Identify what idea(s) shall be taken forward into an implementation plan | Completed | Angela, Pauline, Lesley and Nick | PC and APIT |  |  |  | As above commentary | Completed |
| 3 | The Group with support from the APIT will undertake research which funders may assist with the plan / prepare funding bids / provide costings / installation Plan | 2020 | Angela, Pauline, Lesley and Nick | PC and APIT | £7536 |  | £7536 | Funders have been suggested and noted. Applications to be made for ‘in principal’ funding. Three quotes have been submitted. Plans have been scrutinised and criteria is to be developed for selection of the Park and Contractor. | Delays likely due to COV19 |

| 4 | Explore what opportunities exist within Millom Park Woods to provide a child friendly space within the Estate operated by Lowther Estates. | 2020 | David |  |  |  |  | Contact is planned with Lowther Estates | Work Underway |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C2 | Working with Thwaites School |  |  |  |  |  |  |  |  |
| 1. | Explore what opportunities can be taken forward with the community to support young children’s access to Safe Spaces | 2020 | David and Angela |  |  |  |  | Discussions held the School Governors and Head Teacher – will issue communications to Residents | Work Underway |

|  | MWPC Community Plan – Monitoring Report 18th May 2020 | Target date | Lead Councillors | Who Is working on the action | Project Budget | Allocated or spent to date | Balance to spend | DELIVERY OVERVIEW | RAG STATUS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D | Parish Concerns |  |  |  |  |  |  |  |  |
| D1 | Affordable Housing |  |  |  |  |  |  |  |  |
| 1 | The Parish Council will examine opportunities to explore what schemes are available to promote or support specific housing needs in the community | 2020 | David and Gaby | PC and CBC |  |  |  | Lead Councillors to commence work on this action and agree what can be done at the current stage of Covid-19 | Delays likely due to COV19 |
| 2 | The Parish will raise this issue with Copeland Borough Council and discuss what options are available within new planning developments. | 2020 | David and Gaby | PC and CBC |  |  |  | As above commentary | Delays likely due to COV19 |
| D2 | Derelict Housing |  |  |  |  |  |  |  |  |
| 1 | The Parish Council will identify current housing stock within the Parish which is regarded as derelict and /or empty houses. | Completed | Adrianne | PC and CBC |  |  |  | Information of the stock of derelict housing has been provided to CBC for review and action by CBC | Completed |
| 2 | The PC will continue to work with Copeland BC Empty Homes Officer to support the beneficial use of the lands or buildings. | Action Underway | Adrianne | PC and CBC |  |  |  | CBC are seeking external support to address the legal issues of derelict housing. The pace of this action is dependent upon CBC priorities | Delays likely due to COV19 |
| D3 | Planning Vigilance |  |  |  |  |  |  |  |  |
| 1 | Noting the response from the Community Plan, the PC will consider the merits of undertaking a Neighbourhood Plan as a means to exert more influence on planning issues | 2023 | David and Brian | PC |  |  |  | Work on this action has been delayed. The Team expect to make progress on this issue on the next few months | Work to commence |
| 2 | The PC will review its working arrangements with the Copeland Planning Team so inputs from the PC are completed with maximum impact to Planning Applications. | 2020 | David and Brian | PC with CBC |  |  |  | Two Councillors have attended a CALC Course on planning issues for Parish Councils – further work to be undertaken with CBC Planning Department regarding effective submissions | Delays likely due to COV19 |
| D4 | Improved Street Lighting |  |  |  |  |  |  |  |  |
| 1 | The PC to work with the identified communities seeking additional lighting to identify if and where progress can be made, subject to costs and benefits. (This includes Hallthwaites, The Hill and appropriate lighting to Green Road Station). | 2022 | Gaby | PC with Community Involvement |  |  |  | This action has been impeded by CBC plan to transfer Street Lighting to Parish Councils. A review is underway led by CBC to assess the options. Until this review is complete any further action is not appropriate as this has significant costs and implications for the Parish Council budget. | Delayed by CBC Review of street lighting |
| D5 | Bus Shelters |  |  |  |  |  |  |  |  |
| 1 | The PC will examine the ownership and maintenance liabilities on the current Bus Shelters at The Hill and The Green. | Completed | Jeg | PC and CBC |  |  |  | Positioned agreed by Parish Council to undertake maintenance work on the shelters so as to retain a positive impact on the local landscape | Completed |
| 2 | A fully costed Improvement Plan to be considered by the PC working with the current owners of the bus shelters | Dec 2020 | Jeg | PC and HMP Haverigg | £2000 |  | £2000 | Request made for support from HMP Haverigg to undertake to the labour. Agreed by HMP | Delays likely due to COV19 |
| D6 | Dog Fouling |  |  |  |  |  |  |  |  |
| 1 | PC to ensure residents are aware of the process to report dog fouling via Out and About | Completed | Adrianne |  |  |  |  | Publicity undertaken in March 2020 to explain the options open to Residents. Also refer to Action A2.2 regarding the positioning of new bins | Completed |
| D7 | Visibility of Police |  |  |  |  |  |  |  |  |
| 1 | The Parish will raise this issue with Copeland Borough Council and discuss what options are available within new planning developments. | Completed | David | PC and SCP |  |  |  | Drop in event held – Covid-19 now impact future operations | Delays likely due to COV19 |
| D8 | Tourism |  |  |  |  |  |  |  |  |
| 1 | Working with the Southern Boundary Partnership to explore the feasibility of extending the current boundary of the lake District National Park to include the Duddon Estuary. | Completed | David | PC and SBP |  |  |  | Formal submission to HMG was made in July 19 with a range of community conversations held to explain the new proposed National Park Boundary. HMG is to respond to the submission | Await HMG response |
| D9 | Drains and Sewerage |  |  |  |  |  |  |  |  |
| 1 | The PC to make a formal representation to the appropriate authorities to address the issues of sewerage and drainage infrastructure | Completed | Jeg |  |  |  |  |  |  |
| 2 | The PC to provide information on new septic tank law and suggest practical ways of checking and ensuring compliance. | Dec 2020 | Jeg | PC with CBC |  |  |  | Parishioners meetings postponed due to Covid- 19. Information on new regulations have been shared by Out and About | Delays likely due to COV19 |
| D10 | Interest in Gas |  |  |  |  |  |  |  |  |
| 1 | The PC to discuss with what scope there is to connect to our Parish with consideration to the Government policy for renewable v fossil-based energy sources. | Sept 2020 | Jeg | PC and Cadent Gas |  |  |  | Work is underway | Work is underway |
| D11 | Community Shop |  |  |  |  |  |  |  |  |
| 1 | The PC will discuss with current local mobile shop the potential to cover the area of this Parish | Completed | PC | Angela |  |  |  |  | Completed |

Abbreviations:

| APIT – Action Plan Implementation Team | CPSG – Community Plan Steering Group |
| --- | --- |
| CBC – Copeland Borough Council | GSQLC – Ghyll Scaur Quarry Liaison Committee |
| CCC – Cumbria County Council | PC - Millom Without Parish Council |
| SCP – South Copeland Partnership | SBP – Southern Boundary Partnership |